## Active
Milestone ID | Milestone | Workstream | Owner | Start Date | Due Date | Revised Date | Status | Notes
1 | Staff privacy notice - completed and signed by all staff | Policies and Procedures | JH | 01.01.19 | 31.05.19 |  | G
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45

## Completed
Milestone ID | Milestone | Workstream | Owner | Start Date | Due Date | Revised Date | Status | Notes
1 | Staff privacy notice - completed and signed by all staff | Policies and Procedures | JH | 01.01.19 | 31.05.19 |  | Completed
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45

## Policies and Procedures (hidden)
Code | Work packages activity | Activities | Lead person | Stakeholders | Output | Start date | Review point | Delivery date | Sign off | Status
1_CF | Managing Information Policy | Update data protection policy | KJ | A&R | Policy doc | 2017-10-01 |  | 2017-11-01 | Audit and Risk Committee | Completed
2_CF | Central register for data processing activities |  | DG | Strategic Planning | Spreadsheet | 2017-10-01 | Ongoing | 2018-01-01 | Ongoing
3_CF | Fair Processing Notice |  | KJ |  | Doc | 2017-11-01 | 2018-12-05 | 2017-12-11 | GDPR Project Board
4_CF | Privacy statements |  | KJ | GH | Doc | 2017-11-17 | 2018-12-05 | 2017-12-11 | GDPR Project Board
5_CF | Consent statements |  | KJ | GH | Doc | 2017-11-17 | 2018-12-05 | 2018-12-11 | GDPR Project Board
6_CF | Confirm status of volunteers (data processors or data controller on behalf of GG) | Create document - steering board and BWB | KJ | KJ | Doc | 2017-11-17 | 2018-12-05 | 2017-12-11 | GDPR Project Board
7_CF | 3rd Party Processing Agreement | • Guiding tiers • 3rd party suppliers (processors) | DG | GH | Contract doc | 2017-11-17 | 2018-12-05 | 2017-12-11 | GDPR Project Board
8_CF | Mechanism to put third party agreements in place defined for Tiered Structure |  | KJ with Ops Board and C/R managers | GH | Process doc | 2017-11-25 | 2018-12-05 | 2017-12-11 | GDPR Project Board
9_CF | Mechanism to put third party agreements in place defined for third party suppliers |  | KJ (with relevant teams) | GH | Process doc | 2017-11-25 | 2018-12-05 | 2017-12-11 | GDPR Project Board
10_CF | Data Audit 2 Protecture report | • Department activity plan | Protecture, with input from Workpackage leads | Strategic Planning | Doc | 2017-10-01 |  | 2017-12-01 | KJ
11_CF | Departmental compliant action plans | Work packages | • Protecture • Work package leads | Strategic Planning | Action plan doc | 2017-12-01 |  | 2018-01-05 | RM
12_CF | Clarify approach to processing child data and communication with children under 14) | Child data - can we communicate directly with children?? Are we sending anything to children under 14? | KJ with Protecture | LB / Lisa & Devia & Charlioe | Doc agreement for steering group | 2017-11-20 |  | 2017-11-20 | GDPR Project Board
13_CF | Information management procedures: | Breach management; • Volunteer facing • Data protection way of working | DG | RM | Doc | 2017-11-17 | 2018-12-05 | 2017-12-11 | GDPR Project Board
|  | Individual rights management procedures; • SAR • Portability • Erasure • Rectification • ? | DG | Strategic Planning | Doc | 2017-11-17 | 2018-12-05 | 2017-12-11 | GDPR Project Board
|  | Keeping data safe; • Handling data • Collecting data • Sharing information | DG | Strategic Planning | Doc | 2017-11-17 | 2018-12-05 | 2017-12-11 | GDPR Project Board
14_CF | Data protection Impact Assessments | Review central project management methodology and adapt for DPIAs | KJ | Strategic Planning | Process doc | 2017-12-01 |  | 2018-02-01 | GDPR Project Board
15_CF | Retention schedule | • Identify departmental procedures • IT legacy retention | DG / LD | Strategic Planning | Schedule doc | 2017-10-01 | 2018-12-05 | 2017-12-11 | GDPR Project Board
| Activities | Lead person
| Data retention (including historical safeguarding) • Draft guidance on what data to retain and what to destroy (based on data retention schedule and steer from IICSA project board) | LD, IK and KJ
| Set up mechanisms for capturing historical safeguarding data | IICSA project board
| Communication plan for volunteers (linked to Comms plan above) | Comms
| Activities | Lead person | Stakeholders | Delivery date | Sign off | Status
| Data Audit | KJ / JH |  | Complete
| Training for C/R managers | KJ with Protecture
Review of C/R owned data processing activities (from Data Audit) and identification of actions required to achieve compliance
| C/R compliance action plan implemented | C/R managers (with Chief Commissioners) |  | 2018-01-01

## IT and Systems (hidden)
Code | Work packages activity | Activities | Lead person | Stakeholders | Output | Start date | Delivery date | Sign off | Status
| Mechanism for reviewing, updating and deleting electronic records | Define Girlguiding systems, business owners, method for deletion and agree process:
|  | CRM/GO | LD |  | Process Map & Documentation | 2018-01-01 | 2018-03-01 | GDPR Project Board
|  | Fileservers | LD |  | Process Map & Documentation | 2018-01-01 | 2018-05-01 | GDPR Project Board
|  | Exchange | LD |  | Process Map & Documentation | 2018-01-01 | 2018-05-01 | GDPR Project Board
|  | Active Directory | LD |  | Process Map & Documentation | 2018-01-01 | 2018-05-01 | GDPR Project Board
|  | Office 365 | LD |  | Process Map & Documentation | 2018-01-01 | 2018-05-01 | GDPR Project Board
|  | Hr.net | RM | HR | Process Map & Documentation |  |  | GDPR Project Board
|  | E-days | RM | HR | Process Map & Documentation |  |  | GDPR Project Board
|  | Payroll | RM | HR | Process Map & Documentation |  |  | GDPR Project Board
|  | Access Dimensions (Trading) | MG & MW | Trading | Process Map & Documentation | 2018-01-01 | 2018-05-01 | GDPR Project Board
|  | Access Dimensions (CHQ & TACs) | SW & CF/MW | Finance | Process Map & Documentation | 2018-01-01 | 2018-05-01 | GDPR Project Board
|  | Online Shop | MG & MW | Trading | Process Map & Documentation | 2018-01-01 | 2018-05-01 | GDPR Project Board
|  | Online Print Centre | LB | LB, DG | Process Map & Documentation |  |  | GDPR Project Board
|  | Portfolio Image Library | Marketing | MG, DG | Process Map & Documentation |  |  | GDPR Project Board
|  | L&D tool |  |  | Process Map & Documentation |  |  | GDPR Project Board
|  | Main GG Website | CW/TA | DG | Process Map & Documentation |  |  | GDPR Project Board
|  | TAC websites | CW/TA | RT | Process Map & Documentation |  |  | GDPR Project Board
|  | Cinolla | HR | RT | Process Map & Documentation |  |  | GDPR Project Board
|  | E-learning site(s) |  |  | Process Map & Documentation |  |  | GDPR Project Board
|  | Survey Monkey |  |  | Process Map & Documentation |  |  | GDPR Project Board
|  | Dotmailer | TA | DG | Process Map & Documentation |  |  | GDPR Project Board
|  | Slack | LD/TA |  | Process Map & Documentation | 2018-01-01 | 2018-05-01 | GDPR Project Board
|  | Dropbox | LD |  | Process Map & Documentation | 2018-01-01 | 2018-05-01 | GDPR Project Board
Egress
| Mechanism to ensure right of portability | Define Girlguiding systems, business owners, format in which information can be downloaded/transferred and agree process:
|  | CRM/GO | LD |  | Process Map & Documentation | 2018-01-01 | 2018-03-01 | GDPR Project Board
|  | Fileservers | LD |  | Process Map & Documentation | 2018-01-01 | 2018-05-01 | GDPR Project Board
|  | Exchange | LD |  | Process Map & Documentation | 2018-01-01 | 2018-05-01 | GDPR Project Board
|  | Active Directory | LD |  | Process Map & Documentation | 2018-01-01 | 2018-05-01 | GDPR Project Board
|  | Office 365 | LD |  | Process Map & Documentation | 2018-01-01 | 2018-05-01 | GDPR Project Board
|  | Hr.net | RM | HR | Process Map & Documentation |  |  | GDPR Project Board
|  | E-days | RM | HR | Process Map & Documentation |  |  | GDPR Project Board
|  | Payroll | RM | HR | Process Map & Documentation |  |  | GDPR Project Board
|  | Access Dimensions (Trading) | MG & MW | Trading | Process Map & Documentation | 2018-01-01 | 2018-05-01 | GDPR Project Board
|  | Access Dimensions (CHQ & TACs) | SW & CF/MW | Finance | Process Map & Documentation | 2018-01-01 | 2018-05-01 | GDPR Project Board
|  | Online Shop | MG & MW | Trading | Process Map & Documentation | 2018-01-01 | 2018-05-01 | GDPR Project Board
|  | Online Print Centre | LB | LB, DG | Process Map & Documentation |  |  | GDPR Project Board
|  | Portfolio Image Library | Marketing | MG, DG | Process Map & Documentation |  |  | GDPR Project Board
|  | L&D tool |  |  | Process Map & Documentation |  |  | GDPR Project Board
|  | Main GG Website | CW/TA | DG | Process Map & Documentation |  |  | GDPR Project Board
|  | TAC websites | CW/TA | RT | Process Map & Documentation |  |  | GDPR Project Board
|  | Cinolla | HR | RT | Process Map & Documentation |  |  | GDPR Project Board
|  | E-learning site(s) |  |  | Process Map & Documentation |  |  | GDPR Project Board
|  | Survey Monkey |  |  | Process Map & Documentation |  |  | GDPR Project Board
|  | Dotmailer | TA | DG | Process Map & Documentation |  |  | GDPR Project Board
|  | Slack | LD/TA |  | Process Map & Documentation | 2018-01-01 | 2018-05-01 | GDPR Project Board
|  | Dropbox | LD |  | Process Map & Documentation | 2018-01-01 | 2018-05-01 | GDPR Project Board
Egress
| Mechanism to ensure right of rectification | Define Girlguiding systems, business owners, how records will be updated:
|  | CRM/GO | LD |  | Process Map & Documentation | 2018-01-01 | 2018-03-01 | GDPR Project Board
|  | Fileservers | LD |  | Process Map & Documentation | 2018-01-01 | 2018-05-01 | GDPR Project Board
|  | Exchange | LD |  | Process Map & Documentation | 2018-01-01 | 2018-05-01 | GDPR Project Board
|  | Active Directory | LD |  | Process Map & Documentation | 2018-01-01 | 2018-05-01 | GDPR Project Board
|  | Office 365 | LD |  | Process Map & Documentation | 2018-01-01 | 2018-05-01 | GDPR Project Board
|  | Hr.net | RM | HR | Process Map & Documentation |  |  | GDPR Project Board
|  | E-days | RM | HR | Process Map & Documentation |  |  | GDPR Project Board
|  | Payroll | RM | HR | Process Map & Documentation |  |  | GDPR Project Board
|  | Access Dimensions (Trading) | MG & MW | Trading | Process Map & Documentation | 2018-01-01 | 2018-05-01 | GDPR Project Board
|  | Access Dimensions (CHQ & TACs) | SW & CF/MW | Finance | Process Map & Documentation | 2018-01-01 | 2018-05-01 | GDPR Project Board
|  | Online Shop | MG & MW | Trading | Process Map & Documentation | 2018-01-01 | 2018-05-01 | GDPR Project Board
|  | Online Print Centre | LB | LB, DG | Process Map & Documentation |  |  | GDPR Project Board
|  | Portfolio Image Library | Marketing | MG, DG | Process Map & Documentation |  |  | GDPR Project Board
|  | L&D tool |  |  | Process Map & Documentation |  |  | GDPR Project Board
|  | Main GG Website | CW/TA | DG | Process Map & Documentation |  |  | GDPR Project Board
|  | TAC websites | CW/TA | RT | Process Map & Documentation |  |  | GDPR Project Board
|  | Cinolla | HR | RT | Process Map & Documentation |  |  | GDPR Project Board
|  | E-learning site(s) |  |  | Process Map & Documentation |  |  | GDPR Project Board
|  | Survey Monkey |  |  | Process Map & Documentation |  |  | GDPR Project Board
|  | Dotmailer | TA | DG | Process Map & Documentation |  |  | GDPR Project Board
|  | Slack | LD/TA |  | Process Map & Documentation | 2018-01-01 | 2018-05-01 | GDPR Project Board
|  | Dropbox | LD |  | Process Map & Documentation | 2018-01-01 | 2018-05-01 | GDPR Project Board
Egress
| CRM and GO access protocols (schedule of who is entitled to access what data) | Key Entity data list | CF |  | Documentaiton | 2018-12-01 | 2017-03-01 | GDPR Project Board
|  | Key Field data list | CF |  | Documentaiton | 2018-12-01 | 2017-03-01 | GDPR Project Board
|  | Entity link map | CF |  | Documentaiton | 2018-12-01 | 2017-03-01 | GDPR Project Board
|  | Key View data list | CF |  | Documentaiton | 2018-12-01 | 2017-03-01 | GDPR Project Board
|  | Download list | CF |  | Documentaiton | 2018-12-01 | 2017-03-01 | GDPR Project Board
|  | Document Core Pack download templates | CF |  | Documentaiton | 2018-12-01 | 2017-03-01 | GDPR Project Board
| Data security review (from Data Audit 2) findings from Protecture | Activity plan | Protecture & work plan leads | IT & Systems | Documentaiton | 2018-12-01 | 2018-01-01 | GDPR Project Board
| IT system changes prioritised and implemented/planned for future implementation | Fileservers - rationalisation and search ability | LD | GG Teams | Proposal - Process & Tool | 2018-12-01 | 2018-05-01 | GDPR Project Board
|  | Exchange - rationalisation and search ability | LD | GG Teams | Proposal - Process & Tool | 2018-12-01 | 2018-05-01 | GDPR Project Board
|  | Define systems and requirements from Data Audit | TBC | TBC | TBC | TBC | TBC
| Starters, Leavers and Movers (SLaM) process | Define process for Staff | LD & CF | HR, Finance, Facilities | Process Map | 2018-01-01 | 2018-05-01 | GDPR Project Board
|  | Define process for National Level Volunteers | LD & CF | TBC | Process Map | 2018-01-01 | 2018-05-01 | GDPR Project Board
| IT Policies and Procedures | Bring your own device guide/policy | LD | GH | Documentaiton | 2018-01-01 | 2018-05-01 | GDPR Project Board
|  | Acceptable use policy to define who has a GG account and what/how systems will be accessed | LD | GH | Documentaiton | 2018-01-01 | 2018-05-01 | GDPR Project Board
|  | Password policy | LD | GH | Documentaiton | 2018-01-01 | 2018-05-01 | GDPR Project Board
|  | Clear desk, clear screen policy and secure waste policy (IT security) | LD | GH | Documentaiton | 2018-01-01 | 2018-05-01 | GDPR Project Board
|  | Off site, working and removable media policy | LD | GH | Documentaiton | 2018-01-01 | 2018-05-01 | GDPR Project Board
|  | Access control policy | LD | GH | Documentaiton | 2018-01-01 | 2018-05-01 | GDPR Project Board
|  | Back up procedures | LD | GH | Documentaiton | 2018-01-01 | 2018-05-01 | GDPR Project Board
| Security Improvements | Network access control | LD | GH
|  | Office 365 Security | LD | GH | System secuirty best practice | 2018-02-01 | 2018-04-01
|  | MFA to Mail | LD | GH | MFA | 2018-01-01 | 2018-04-01
|  | MFA to VPN | LD | GH | MFA | 2018-01-01 | 2018-04-01
|  | MDM | LD | GH | MDM Tool | 2017-12-01 | 2018-03-01
Document Confidentiality/Rights Management
Data Loss Prevention tools
Data retention technology

## Marketing and Fundraising (hidden)
Activities | Lead person | Stakeholders | Delivery date | Sign off | Status
Review of marketing and Trading and TAC comms processing activities (from Data Audit) and identification of actions required to achieve compliance | TA
Marketing and Trading action plan implemented | TA |  | January-May
Guidance - based on marketing principles and fair processing

## Awareness and Training (hidden)
Activities | Lead person | Stakeholders | Delivery date | Sign off | Status
Develop comms plan to raise volunteer awareness and understanding of new requirements | Comms
Establish GDPR information webpage | KJ HB | KW | November onwards
Review of staff and volunteer learning needs | RN staff and L&D (vols)
Develop scheme of training, information and awareness raising (for relevant levels of volunteer and staff) | L&D team / Comms
Refresh ‘Keeping Data Safe’ information for volunteers | L&D team / Strategic Planning
Develop e-learning pack for GDPR | RN staff and L&D (vols)
Change document for vols and staff re new changes to legislation | DG | RN KW Comms
Items | What | Who | Deadline | Status
1 | Share relevant GDPR information and sign post to relevant training etc | DG/ KJ
2 | Set up briefing/training session for project team (a must MR/ PL/ L&D vol) | DG/ KJ
3 | Set up a meeting to go through all L&D resources Vicky has currently (also with L&D vol) and DG) | MR | 14.12.2017 | Done
4 | Complete membership systems change process request form | MR | End Jan 2018
5 | Complete an MA&E form (for involvement of digitial- web and e-learning and commissioning) | MR | 14.12.2017 | Done
6 | Write short paper on compliance for GDPR and L&D | EH
7 | Put above paper on next GDPR board meeting agenda for Jan | KJ
8 | Stream of work changed to 'Learning and development of GDPR for volunteers' | KJ
9 | Set meeting with new Programme manange as soon as they start (perhaps with MR and Rebecca? In the first instance ) | KJ
10 | Liasie re: a piece of communication on GDPR heads up for Jan 2018 | KJ and PL
11 | Liaise with Laura to create a communications plan for GDPR | PL
12 | Begin liasion with various other L&D streams to idenity opportunities for embedding (eg LQ/ YLQ/GAW) | MR | 2018-01-01

## Policies and Procedures Plan (hidden)
Milestone ID | Milestone | Workstream | Owner | Start Date | Due Date | Revised Date | Privacy Statement Required? | Status | Notes | Column1
| Country & Region compliance pack | Policies and Procedures | Kathryn Jackson
| Review draft CR pack including 3rd party agreements | Policies and Procedures | JH
| Finalised CR pack - make regional | Policies and Procedures | LM
| Policy & Procedures (including forms) | Policies and Procedures | Kathryn Jackson
| Volunteer Procedures Review | Policies and Procedures | LM
| Copy editor reviewing policies and procedures | Policies and Procedures | BD
| Review new staff policies | Policies and Procedures | JH & HR Committee
| Management Information Policy feedback at Ops Board | Policies and Procedures | JH
| Create a procedure for reviewing data protection compliance | Policies and Procedures | BD & LM
| IT security breach process to align with data breach process | Policies and Procedures/IT and Systems | BD
| Managing Information Policy to go to Board of Trustees | Policies and Procedures | JH & LM
| Update employment contract - Protecture advice | Policies and Procedures | HQ, JH & HRServices
| Privacy Notice | Policies and Procedures | Dave Gibbons
| Privacy Notice reviewed including digital content (due at C/R managers meeting) | Policies and Procedures | JH
| Add privacy notice to website | Policies and Procedures | BD | 24.05.18 | 30.06.18
| 3rd Party Processing Agreement | Policies and Procedures | Dave Gibbons
| Review 3rd party processing agreement template from Girlguiding | Policies and Procedures | JH
| Sign off 3rd party processing agreement with Girlguiding | Policies and Procedures | Trustees
| Create Anglia 3rd party agreement for own contracts / partnerships | Policies and Procedures | JH & LM | 2018-06-01 | 2018-08-31 |  |  | G
| A checklist to be written what to look for in contracts (processing requirements) | Policies and Procedures | JH
| Review all contacts with 3rd party processers | Policies and Procedures | JH
| Correlate changes made to document to determine which depts. need agreements put into place (to be actioned as ammendments to exisiting contactural terms) | Policies and Procedures | JH | [6 empty] | .
| Draft an email for heads of dept. to send to these providers asking for their process | Policies and Procedures | JH
| Agreements in place for all suppliers | Policies and Procedures | JH
| Joint Data Controller Agreement (JDCA) | Policies and Procedures | Kathryn Jackson
| First draft Joint Data Controller Agreement reviewed | Policies and Procedures | JH
| Review with legal advice | Policies and Procedures | JH
| Present JDCA to trustees with advice received for ratifictaion | Policies and Procedures | JH & LM
| Sign JDCA and return to Girlguiding | Policies and Procedures | Trustees via LM
| Data Protection (Website & Publications) | Policies and Procedures
| Review present photo permissions (electronic and printed) | Policies and Procedures + Digital Team | BD | 29.05.18 | 31.09.18
| Commission new photos following updated permission guidance | Policies and Procedures + Digital Team | BD | 24.05.18 | 31.12.18 |  |  |  | This includes all new photos for website. A new permissions will be created for use following GDPR
| Create photo tracking procedure | Policies and Procedures | BD |  | 31.09.18
| Implement permission tracking and storage procedures | Policies and Procedures | BD |  | 31.09.18
| Update photo/video consent form. |  | BD |  | 31.09.18
| Data collection forms review | Policies and Procedures | Managers
| Create standard email conventions including signatures & out of office | Policies and Procedures | BD |  | 31.07.18 |  | yes
| Review data protection statements on documents across departments | Policies and Procedures | BD |  | 31.07.18 |  | yes
| Prep data statement for all collection forms (based on the privacy statement) | Policies and Procedures | BD |  | 31.07.18 |  | yes
| Update all forms and train staff in use | Policies and Procedures | BD |  | 31.07.18 |  | yes
| Data Protection Impact Assessment | Policies and Procedures
| Implement Data Protection Impact assessment for all projects | Policies and Procedures | KS
| Develop DPIA procedure | Policies and Procedures | KS
| Central Register of Processing | Policies and Procedures
| Create register of data processing activities, including 3rd parties | Policies and Procedures | Managers |  | 31.07.18 |  | yes
| Activity Centres compliance pack | Policies and Procedures
| Review finalised pack from Girlguiding | Policies and Procedures | FH
| Quirey and action pack as required. | Policies and Procedures | FH

## Communications Plan (hidden)
Milestone ID | Milestone | Workstream | Owner | Start Date | Due Date | Revised Date | Privacy Statement Required? | Status | Notes
1 | GDPR/ICSA Letter sent to members | Communications | HQ
1.1 | Review GDPR letter sent to members | Communications | BD |  |  |  |  | completed
1.2 | Update volunteer induction in line with new GDPR guidance | Communications | LM |  | 04.09.18 |  | yes | Completed
2 | Delivery of ongoing communications to members | Communications | HQ & BD |  | 31.12.18
2.1 | Creation of comms plan for region members | Communications | BD | 29.05.18 | 31.07.18 |  | yes
2.2 | Chase comms plan for counties from HQ | Communications | JH
2.3 | Create support plan from region to go out to counties | Communications | BD | 22.05.18 | 31.12.18
| Recruitment Packs | Communications | LM/BD |  | 31.07.18 |  | yes | Completed

## IT Systems Plan (hidden)
Milestone ID | Milestone | Workstream | Owner | Start Date | Due Date | Revised Date | Privacy Statement Required? | Status | Notes
| Update Acceptable Use Policy | IT and Systems | HQ, JH & LM |  |  |  |  | Completed
| Create a process for reviewing access rights | IT and Systems | JH & LM
| Review and monitor HQ preference centre for marketing/fundraising comms | IT and Systems/Marketing and Fundraising | BD
| Review lifecycle of staff access | IT and Systems/Policies and Procedures | LM
| Password policy set and added to staff procedures | IT and Systems/Policies and Procedures | LM |  |  |  |  | Completed
| Monitor changes to CRM user sheet incl. password policies | IT and Systems | BD (via CN) | 25.05.18 | 31.12.18 |  | yes
| Include in the access control recommendation above detail of how access to websites is managed; include a current list of which roles have access to which websites and portals, and review this against their need to have access, making any changes as required. | IT and Systems | LM
| Backup procedure and mapping to be received from AIT | IT and Systems | JH
| IT to develop a back up schedule based on Protecture advice - check with AIT | IT and Systems | JH
| Surveys - check agreement licences | IT and Systems | BD |  | 31.07.18 |  | yes
| Check document management sites agreement licences (dropbox) | IT and Systems | BD |  | 31.07.18 |  | yes
| 3rd party remote access systems looked at | IT and Systems | JH
| Develop convention process for G drive | IT and Systems | LM |  | 2018-12-31 |  |  | G
| Implement common saving / convention system for office drives with all staff | IT and Systems | LM |  | 2018-12-31 |  |  | G
| Implement annual data clense schedule and process | IT and Systems | LM, FH & LC
| Retention schedule - update convention from updated archiving guidance from Girlguiding | IT and Systems | LM
| Audit all IT equipment and specifications | IT and Systems | LM |  |  |  |  | Completed
| Create and implement secure IT disposal procedure | IT and Systems | BD |  | 31.08.18
| Implement annual review of software and removal / retention process | IT and Systems | LM |  | 30.06.18 |  |  | Completed

## L&D Staff (hidden)
Milestone ID | Milestone | Workstream | Owner | Start Date | Due Date | Revised Date | Privacy Statement Required? | Status | Notes
| Training for permanent/ Fixed term staff/Casual Staff/Seasonal Staff | L&D Staff | Rebecca Nuttall
| All staff have completed introductory GDPR module | L&D Staff | JH |  |  |  |  | Completed
| Send GDPR module 2 to all staff and reminder about the first module when received from Rebecca Nuttall | L&D Staff | JH
| All staff have completed GDPR module 2 | L&D Staff | JH
| Chase any outstanding staff (after 2 weeks all staff and then SMT) | L&D Staff | JH |  |  |  |  | Completed
| Confirm process and timeframe for regular elearning refreshers set by Girlguiding | L&D Staff | JH
| Update Induction Process | L&D Staff | JH & BD
| Include Acceptable Use Policy in staff induction process | L&D Staff | LM |  |  |  |  | Completed
| Agree which policies new starters need and the process to send them | L&D Staff | LM |  | 2018-09-30 |  |  | G
| Agree which e-learning module new starters need to complete and how long they have to do it | L&D Staff | LM |  |  |  |  | Completed
| Agree process for chasing new starters | L&D Staff | LM |  |  |  |  | Completed
| Set up monthly reminder for chasing new staff | L&D Staff | LM |  |  |  |  | Completed
| Refresher training/ Follow up | L&D Staff
| Review requirement for GDPR to form part of annual appraisals | L&D Staff | JH & BD
| Data protection training | L&D Staff | LM/BD |  | 30.09.18
| Existing staff complete e-learning | L&D Staff | JH |  | 31.05.18
| Staff induction to include e-learning prior to system use | L&D Staff | LM |  | 30.09.18 |  |  | Completed
| Terms of use agreement for all staff | L&D Staff | HR
| Acceptable user policy for ratifying by HR | L&D Staff | JH
| Check contract terms and conditions re data protection | L&D Staff | HR/JH
| Refresher training added to staff meeting rolling agenda | L&D Staff | LM/BD |  | 30.09.18
| Staff file annual update | L&D Staff | JH/BD/FH/LC |  | 31.01.19
| Review leaver exit interview in relation to data protection | L&D Staff | LM/JH
| Explore sage payroll process in line with guidance | L&D Staff | JD
| Staff working practices | L&D Staff | JH/BD/FH/LC
| End of email convention created and added to all signatures | L&D Staff | BD
| Clear desk policy implemented with check system in place | L&D Staff | BD | 01.06.18 | 31.08.18
| Transporting data (USB) system implemented / privacy storage procedure | L&D Staff | LM | 01.06.18 | 2018-09-30 |  |  | G
| BYO |  | JH
| Develop / confirm unattended equipment policy/procedure |  | JH
| Volunteers - consider impact | L&D Staff | BD/JH |  | 31.08.18
| Guidence circulated regarding internal communications | L&D Staff | BD |  | 31.08.18
| Central storage system | L&D Staff | BD/LM/JH |  | 30.09.18
| Bring your own device' staff and volunteer policy sourced from Girlguiding | L&D Staff | JH
| Source Girlguiding example of supplier/customer/client relationship agreement | L&D Staff | JH
| Unauthorised access to information | L&D Staff | BD |  | 30.09.18
| Secure (locked) print procedure implemented and training provided as required | L&D Staff | LM |  | 2018-09-30 |  |  | Completed
| Out of office template standardised | L&D Staff | BD |  | 31.07.18
| Review access to master keys | L&D Staff | LM |  | 2018-09-30 |  |  | G
| Controlled access to devices implemented | L&D Staff | LM
| Individual master email lists made and kept securely | L&D Staff | LM/BD |  | 30.09.18
| Personal information sharing |  | BD |  | 30.09.18
| Sharing information staff and volunteer procedures formalised |  | BD |  | 30.09.18
| Anonimised data procedures formalised |  | BD |  | 30.09.18

## L&D Volunteers (hidden)
Milestone ID | Milestone | Workstream | Owner | Start Date | Due Date | Revised Date | Privacy Statement Required? | Status | Notes
| Create project plan, set up project documentation and 'ways of working' and secure all relevant stakeholder involvement | L&D (volunteers) | HQ | 2018-01-19 | 28.02.2018 |  |  | A
| Draft basic project plan and shared for comment (lead vol and GDPR PM) | L&D (volunteers) | HQ |  |  |  |  | Completed
| Monthly/fortnightly 'progress meetings' set up and chaired by PM | L&D (volunteers) | BD |  | 31.07.18 |  |  | Completed
| Set up location for shared documentation and set up relevant logs etc (inclu how to keep Lead vol in loop) | L&D (volunteers) | LM |  |  |  |  | Completed
| Project plan agreed by core team and implementaion team (includes risk assessment, change management etc) | L&D (volunteers) | BD & Team |  | 31.08.18 |  |  | A
| Budget clarified and signed off | L&D (volunteers) | BD, JD & JH |  | 31.08.18 |  |  | A
| Clarify learning needs and briefing/training on GDPR for those involved | L&D (volunteers) |  | 12.02.2018 | 28.02.2018 |  |  | A
| Kathryn gathering and sharing consultation with commissioners and volunteers to provide context and 'what vols need to know/are concerned about' | L&D (volunteers) | BD |  | 30.09.18 |  |  | A
| Content experts brief/train those involved and share all required documentation | L&D (volunteers) | BD |  | 30.09.18 |  |  | Completed
| PM review all supplied documentation | L&D (volunteers) | BD |  | 30.09.18 |  |  | Completed
| Create communicatons plan and other comms elements | L&D (volunteers) and Communication plan |  | 12.02.2018 | 28.02.2018 |  |  | Not Started
| Comms team draft a 'comms plan' in close liasion with PM | L&D (volunteers) and Communication plan | HQ & BD |  | 30.09.18
| Draft FAQs for info team and share | L&D (volunteers) | HQ & BD |  | 30.06.18
| Scope option of creating a promotional video on GDPR | L&D (volunteers) | BD |  | 30.09.18
| County & Plans |  | BD | 22.05.18 | 30.09.18
| Communicate and support take up of GDPR e-learning |  | BD | 01.05.18 | 31.05.18
| All feedback post launch picked up and logged (urgent issues addressed asap, other logged for 2 year review) | L&D (volunteers) | BD | 25.05.18 | 31.12.18 |  |  | Not Started
| Feedback log created | L&D (volunteers) | BD | 25.05.18 | 31.12.18
| Feedback logged and reviewed |  | BD | 25.05.18 | 31.12.18

## Marketing and Fundraising Plan (hidden)
Milestone ID | Milestone | Workstream | Owner | Area Lead | Start Date | Due Date | Revised Date | Privacy Statement Required? | Status | Notes
| Preference centre and email marketing | Marketing and Fundraising |  |  |  | tbd |  |  | R
| Get quotes for Preference Centre & email marketing project | Marketing and Fundraising | BD to review HQ work |  | 2018-02-01 | 2018-02-09 |  |  | G
| Clarify project and support from Dotmailer (email marketing provider) | Marketing and Fundraising | BD to review HQ work |  | 2018-02-01 | 2018-02-28 | 30.06.18 |  | G
| Requirements gathering for Preference Centre | Marketing and Fundraising | BD to review HQ work |  | 2018-02-01 | 2018-02-28 | 31.05.18 |  | G
| Implementation for Preference Centre | Marketing and Fundraising | BD to review HQ work |  | 2018-03-01 | 2018-03-31 |  |  | G
| Review all communications | Marketing and Fundraising | BD to review HQ work |  | 2018-02-01 | 2018-02-28 | 30.06.18 |  | A
| Define consent categories | Marketing and Fundraising | BD to review HQ work |  | 2018-02-01 | 2018-02-23 | 31.05.18 |  | A
| Finalise proposal external support CRM and preference centre | Marketing and Fundraising | BD to review HQ work |  | 2018-02-01 | 2018-02-09 |  |  | Completed | Winners agency support
| Analyse levels of engagement with historic emails for both volunteers and parents | Marketing and Fundraising | BD to review HQ work |  | 2018-02-12 | 2018-02-28 | 31.07.18 |  | Not Started
| Update user journeys with correct T&Cs and optins | Marketing and Fundraising | BD to review HQ work |  | 2018-02-12 | 2018-03-31 | 31.07.18 |  | Not Started
| Confirm what is in the tent and what is out of the tent | Marketing and Fundraising | BD to review HQ work |  | 2018-02-01 | 2018-03-31 | 30.06.18 |  | A
| Confirm 3rd party T&Cs | Marketing and Fundraising | BD to review HQ work |  |  |  | 30.06.18 |  | Not Started
| Confirm parents data set and right use | Marketing and Fundraising | BD to review HQ work |  |  |  | 30.06.18 |  | A
A
| Data entry point audit – forms, surveys, 3rd party sites used over the organisation and what we need to do next (close, delete, remove, support transition etc.) This includes guidelines and support on how to transition. | Marketing and Fundraising | BD to review HQ work |  |  |  | 30.09.18 |  | G
| Data entry point audit follow up and actions - (close, delete, remove, support transition etc.) This includes guidelines and support on how to transition. | [5 empty] | 30.09.18
| Surveys – survey monkey, doodle, web forms. Process and policy development | Marketing and Fundraising | BD to review HQ work |  |  |  | 31.07.18 |  | A
| Preference centre - build support | Marketing and Fundraising | BD to review HQ work |  |  |  | 31.07.18 |  | A
| Email marketing - guidance, guidelines and how to guide for staff and C&Rs | Marketing and Fundraising | BD to review HQ work |  |  |  | 31.07.18 |  | A
| County and below – guidance and guidelines for marketing and sending communications | Marketing and Fundraising | BD to review HQ work |  |  |  | 31.07.18 |  | A
| Re-opt in campaign - Creative concept development and action | Marketing and Fundraising | BD to review HQ work |  |  |  | 31.07.18 |  | A
| Photo consent – images on portfolio, website(s), presentations, 3rd party sites, social (policy and process) | Marketing and Fundraising | BD to review HQ work |  |  |  | 31.07.18 |  | A
| Privacy statement - fit for purpose for user journey and consistency on all print | Marketing and Fundraising | BD to review HQ work |  |  |  | 31.07.18 |  | A
| Auto comms from sign up journey – amend all copy | Marketing and Fundraising | BD to review HQ work |  |  |  | 31.07.18 |  | A
| Print forms – working with Dave to ensure consistency and opt-ins | Marketing and Fundraising | BD to review HQ work |  |  |  | 31.07.18 |  | A
| 3rd party sites - opt-ins and links to T&CS/privacy policy | Marketing and Fundraising | BD to review HQ work |  |  |  | 31.07.18 |  | A
| Filing system - M&AE / U drive / S drive | Marketing and Fundraising | BD to review HQ work |  |  |  | 31.07.18 |  | A
| Internal comms strategy – including all messages and actions needed by staff (we are still working on the content which staff need to know and the actions they need to be aware of) | Marketing and Fundraising | BD to review HQ work |  |  |  | 31.07.18 |  | A
| C&Rs continued support – email marketing, photos | Marketing and Fundraising | BD to review HQ work |  |  |  | 31.07.18 |  | A
| Data processor agreements for all departments (guidance on 3rd party sites) | Marketing and Fundraising | BD to review HQ work |  |  |  | 31.07.18 |  | A
| Website T&Cs + cookie statement – ensure on website, shop and TACs and fit for purpose under GDPR | Marketing and Fundraising | BD to review HQ work |  |  |  | 31.07.18 |  | A
| Dotmailer service emails – suppression list removal | Marketing and Fundraising | BD to review HQ work |  |  |  | 31.07.18 |  | A
| Ensuring BAU communications are compliant | Communications | BD follow HQ lead |  |  | 2018-04-27 |  |  | A
| Confirm 'in vs out' of the tent for membership communications | Communications | BD to review HQ work |  | 2018-02-01 | 2018-02-23 | 31.07.18 |  | A
| Create guiidelines for BAU memebr comms compliance based on the above | Communications | BD to review HQ work |  | 2018-02-23 | 2018-03-08 | 31.07.18 |  | A
| Confirm data on current audiences for Discover, grow | Communications | BD to review HQ work |  | 2018-02-12 | 2018-02-23 | 31.07.18 |  | A
| Confirm data on current audiences for YeSS | Communications | BD to review HQ work |  | 2018-02-12 | 2018-02-23 | 31.07.18 |  | A
| Confirm approach to unsubscribe option from all member comms | Communications | BD to review HQ work |  | 2018-02-23 | 2018-03-31 | 31.07.18 |  | A
| Resubscribe members to essential comms once approach confirmed, plus communciation explaining | Communications | BD to review HQ work |  | 2018-02-23 | 2018-04-27 | 31.07.18 |  | A
| Send communication to all members on our GDPR compliance and what they can expect from us | Communications | BD to review HQ work |  | 2018-02-23 | 2018-04-27 | 31.07.18 |  | A
| Amend all footers | Communications | BD to review HQ work |  | 2018-02-23 | 2018-04-27 | 31.07.18 |  | A
| Development of member email marketing strategy | Communications | BD to review HQ work |  | 2018-02-23 | 2018-04-27 | 31.07.18 |  | A
| Digital eco-system | Marketing and Fundraising | BD follow HQ lead |  |  | tbd |  |  | A
| Audit of all online data entry points | Marketing and Fundraising | BD to review HQ work |  | 2018-02-01 | 2018-02-28 | 31.07.18 |  | A
| Reviewing privacy notice from IT and Digital perspective | Marketing and Fundraising | BD to review HQ work |  | 2018-02-09 |  | 31.07.18 |  | Not Started
| Audit and review of 'other tools' used i.e. Survey Monkey and Google forms | Marketing and Fundraising | BD to review HQ work |  | 2018-02-01 | 2018-02-28 | 31.07.18 |  | R
| Restrict access to Surveymonkey, delete data and increase security and acccess to account with IT | Marketing and Fundraising | BD to review HQ work |  |  |  | 31.07.18 |  | A
| Build webform functionality and right opt-in messaging to the main site | Marketing and Fundraising | BD to review HQ work |  |  |  | 31.07.18 |  | A
| Updating digital platforms that aren't compliant (webshop, donation platform etc) | Marketing and Fundraising | BD to review HQ work |  |  |  | 31.07.18 |  | A
| Digital procurment process elearning tool | Marketing and Fundraising | BD to review HQ work |  |  |  | 31.07.18 |  | A
| 3rd party donate pages changes i.e Just giving | Marketing and Fundraising | BD to review HQ work |  |  |  | 31.07.18 |  | A
| Change cookie statement - active opt-in (main site, donate, TAC and future webshop) | Marketing and Fundraising | BD to review HQ work |  |  |  | 31.07.18 |  | A
| Data export from new webshop of people who have donated? | Marketing and Fundraising | BD to review HQ work |  |  |  | 31.07.18 |  | A
| Agree on email optin yes or now for the new webshop | Marketing and Fundraising | BD to review HQ work |  |  |  | 31.07.18 |  | A
| Work with IT on pentesting main site and TAC site | Marketing and Fundraising | BD to review HQ work |  |  |  | 31.07.18 |  | A
| Data in CMS - review this and make sure it is part of policies | Marketing and Fundraising | BD to review HQ work |  |  |  | 31.07.18 |  | A
| Dropbox license agreement |  | BD |  |  |  | 31.07.18
| Create privacy documents for all paper and elect documents (incl. financa and regulatory work) |  | BD |  |  | 31.07.18
| Implement privacy document use |  | BD |  |  | 30.06.18
| Source / create social media policy |  | BD |  |  | 30.06.18
| Develop process for cascading changes to lead volunteers (photos / docs etc) |  | BD |  |  | 30.06.18
| Implement process for cascading changes to lead volunteers (photos / docs etc) |  | BD |  |  | 30.06.18

## Preference Centre (hidden)
Milestone | Owner | Start Date | End Date | Status | time axis 2018-03-12 to 2018-05-25

## Risks (hidden)
Risk ID | Likelihood | Severity | Risk | Workstream | Mitigation | Owner | Due Date | Post Mitigation Status | Notes
1 | High | High | People's marketing and fundrasing preferences are not stored anywhere so communications may be sent to people who have opted out causing a breach of GDPR leading to reputational and financial impact. | Marketing and Fundraising | Implement a preference centre which stored communication preferences and can be accessed by anyone who sends communications | Devia Gurjar | 2018-05-25 | Low
2 | Medium | High | The countries and regions are separate charities so their staff are not governed by our policies and procedures, if their staff are not correctly trained on data protection they could cause breach leading to reputational and financial impact | Policies and Procedures | Create Joint Data Controller Agreement for countries and regions to sign which makes clear their responsibility to comply with GDPR and the consequences if they don't do so. | Ruth Marvel | 2018-02-09 | Medium
3 | Medium | High | Loss of key personel leads to project delays, impacting our compliance with GDPR potentially causing reputational, financial and legal risk. Key Staff: Project Manager: Chantal Wood Data Protection Lead: Dave Gibbons Comms Lead: Charlie Wells IT/Systems Lead: Lisa Dalton L&D Staff Lead: Rebecca Nuttall L&D Volunteer Lead: Mira Ruskin Policy and Procedures Lead: Kathryn Jackson | Programme | Loss of key personel leads to project delays, impacting our compliance with GDPR potentially causing reputational, financial and legal risk. Cover Project Manager: None Data Protection Lead: Kathryn Jackson Comms Lead: Devia Gurja IT/Systems Lead: Martin Wilson L&D Staff Lead: Heather Stronestreet L&D Volunteer Lead: ? Policy and Procedures Lead: Ruth Marvel | Gary Hocking | Ongoing | High
4 | Medium | Medium | A broad definition of 'In the tent' content for compulsory email communication may lead to volunteers perceiving the information they recieve as marketing which could result in a complaint to the ICO leading to reputational and financial impact | Marketing and Fundraising | Define comms guideline for communication after the deadline to ensure that communications can't be construed as marketing by recipients. | Devia Gurjar | 2018-02-26 | Low
5 |  | High | dotMailer may monitor content of service emails and prevent us from sending commercial content which we havee deemed in the tent. This coul dhave financial impact. | Marketing and Fundraising | Find out if dotmail monitor content | Devia Gurjar | 2018-02-26
6 | High | High | HQ staff lack the capacity to understand GDPR and make appropriate changes to procedures to be compliant in their day to day work, this could cause a breach leading to reputational and finance impact. | Programme | The Data Protection lead are running audits with each team to help the understand what changes they need to make. New eLearning has been rolled out and is compulsory for all staff. There will be an introduction to GDPR in Team Time in March | Gary Hocking | 2018-05-25 | Low
7 | Medium | High | CRs don't sign the JDCA before May 25th so we have no legal agreement enforcing how GO data should be used, this could cause a breach of GDPR leading to reputational and financial impact | Policies and Procedures | The JDCA is being finalised so it can be sent to CR manager with plenty of time before the deadline so that any questions and concerns can be dealth with. Consequences for not signing the agreement are being considered, this could include losing access to GO. | Ruth Marvel |  | Medium
8 | Medium | High | CR staff do not complete the GDPR eLearning module so do not understand how to comply with GDPR, this could cause a breach leading to reputational and finance impact. | L&D - Staff | HR are working with CR to ensure all CR staff are set up on the eLearning system. The JDCA stipulates that all CR staff must complete the eLearning. | Gary Hocking |  | Medium
9 | Medium | High | HQ staff do not complete the GDPR eLearning module so do not understand how to comply with GDPR, this could cause a breach leading to reputational and finance impact. | L&D - Staff | Staff are required to complete the module by the end of the month and HR are working with SMT to ensure compliance. | Gary Hocking |  | Low
10
11
12
13
14
15
16
17
18
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52

## Issues (hidden)
Issue ID | Severity | Issue | Worksteam | Actions | Owner | Date | Status? | Notes
1 | R | We do not currently have permission to send marketing emails to parents | Marketing and Fundraising | Stop sending communications to parents until we have the ability to collect and store their marketing preferences. | Devia Gurjar | tbd dependant on prefreence centre work | A | Amber rating reflects uncertainty around preference centre timeline
2 | R | We can't send emails to all volunteers through dotMailer because some have unsubscribed from communications | Marketing and Fundraising | dotMailer have confirmed we can send service emails which bypass the unsubscribe mechnism. The comms team are working on using this functionality so we can send email comms to volunteers re GDPR. | Charlie Wells | 2018-03-19 | G
3 | R | Some data entry points have marketing opt-outs/do not display our T+Cs and privacy notice, breaching GDPR. | Marketing and Fundraising | Audit of personal data entry points to determine where there are issues. Removal of opt-outs and additional of correct copy where necssary. | Tessa Adelaar/Chantal Wood | 2018-04-30 | A | Amber rating reflects uncertainty around how many data entry points are non compliant.
4 | R | We are not able to search fileservers for information due to lack of enterprise search tool, meaning we cannot guarentee being able to provide all data for individual rights requests, and do not know what personal data, if any, is being stored on the file server. | IT and Systems | Proof of concept of an enterprise search tool. Deletion of historical data on the fileserver that is no longer in use. | Lisa Dalton |  | A
5 | R | We do not have a system for categorising documents by data type so cannot centrally enforce the retention schedule policy. | IT and Systems | IT investigating options | Lisa Dalton |  | R
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37

## Open Questions (hidden)
Question ID | Question | Team | Reccomendation | Owner | Due Date | Decision | Status? | Notes
1 | How long is consent valid for? | [5 empty] | Open
2 | [6 empty] | Open
3 | [6 empty] | Open
4 | [6 empty] | Open
5 | [6 empty] | Open
6 | [6 empty] | Open
7 | [6 empty] | Open
8 | [6 empty] | Open
9 | [6 empty] | Open
10 | [6 empty] | Open
11 | [6 empty] | Open
12 | [6 empty] | Open
13 | [6 empty] | Open
14 | [6 empty] | Open
15 | [6 empty] | Open
16 | [6 empty] | Open
17 | [6 empty] | Open

## Decisions (hidden)
Decision ID | Owner | Decision | Date | Notes
1 | GDPR Project Board | Invest in a preference centre | 2018-01-25
2
3
4
5
6
6

## Static Data (hidden)
R | Open | High
G | Closed | Medium
A | On Hold | Low
Not Started
Completed